## Sheet1
AIM	connection...					oft...			other...
client \ test	direct	redirect	proxy 1	proxy 2	proxy 3	normal	resume	already-done	utf8	utf16
gaim 1.5
gaim 2.0b3
adium (0.89/libgaim)	check again	check again			check again
adium (1.0/joscar)
AIM 4.7							checksum?
AIM 5.1
AIM 5.9					check again	regression
trillian 3.1
joscar
ichat
kopete itself

	send	receive	both	neither	SEP field :)

	quick progress summary:
	SoC goals have basically been achieved, apart from not knowing the proper icq rendezvous protocol.
	icq transfer messages can be received, but not sent - to send them you'd need more gui stuff and it would complicate things, I bet
	code has not been cleaned up - many silly things have been left as I found them. I've made notes, though, and I'll get around to it eventually.
	messages in chatwindows need to contain the name of the file they're talking about, but doing so breaks the i18n function because it's dumb.
	I still haven't made full use of that thing anyways.
	errortask will still silently take rendezvous error messages, if there are any. there shouldn't be any right now, but that's still bad, because we'll never know.
	there are isues if a transfer is cancelled before the user accepts it. this is hard to fix because we have no control over the accept dialog.

	stuff that's not in the docs:
	in stage 2 proxy, the receiving side does an init send, and the other side does init recv.
	when resuming a transfer, bytesSent is the important value.
	the receiving side sends how many bytes it's got, and if its checksum is right, the sending side sends back the same #.
	if not, it sends 0, and then you have to take the whole file.

	clients that do weird things:
	gaim sends text as utf8, but if you explicitly say you're using utf8, aim 5.9 will choke. if you explicitly say you're using something else, gaim will ignore you.
	so, the safest thing to do right now is to send utf8 implicitly and hope that non-ascii characters don't make aim 5.9 explode.
	adium/joscar does some very nonsensical things, like sending two rendezvous requests. we can't assume that clients will be sane at all now.
	gaim does not understand resuming yet, and will flat-out ignore any requests for it. this sucks, because the transfer will just appear to stall.
	aim 5.9 doesn't like our OFT prompt. it decides that our client isn't good enough and cancels the transfer.
	all official aim clients do not even try to connect directly to me. they always go through a redirect or proxy.